## Sheet1
Sprint 1
Days | Work Left (Hours) | Expected Work Left (Hours) |  | Jesaiah Prayor | Deoburton Guyadin | Elisee Augustin | Michel Chema | Prateek Malli
2017-05-11 | 85 | 90 | Hours Worked On the Project | 6 Hour | 6 Hours | 6 Hours
2017-05-12 | 82 | 84
2017-05-13 | 82 | 78
Jesaiah Prayor: Involved with planning the workLoad and how the project will perform/Starts Implementing and researching how to build a Module.
Deoburton Guyadin: Involved with planning the workLoad and how the project will perform/ Researched and reviewed code for retrieval of data from National Library of Medicicne API.
Elisee Augustin: Involved with planning the workLoad and how the project will perform/ Researched and reviewed code on Spring MVC Framework.
Prateek Malli: Involved with planning the workLoad and how the project will perform/
Michel Chemas:Involved with planning the workLoad and how the project will perform/
Sprint 2
Days | Work Left | Expected Work Left |  | Jesaiah Prayor | Deburton Guyadin | Elisee Augustin | Michel Chemas | Prateek Malli
2017-05-14 | 77 | 72 | Hours Worked On the Project | 12 Hours | 17 Hours | 7 hours | 5 hours
2017-05-15 | 75 | 66
2017-05-16 | 72 | 60
Jesaiah Prayor: Decides to switch to API, Worked on retrieving required data from National Library of Medicine API using REST.
Deoburton Guyadin: Decides to switch to Module, Researched and installed required OpenMRS programs. (OpenMRS SDK, Maven, OpenMRS Reference Applicaton 2.6.0)
Elisee Augustin: Developed and programmed sample SpringMVC programs for research purpose for future implementation. Difficulty Arises
Prateek Malli:
Michael Chemas: Researched OpenMRS environment and requirements.
Sprint 3
Days | Work Left | Expected Work Left |  | Jesaiah Prayor | DeoBurton Guyadin | Elisee Augustin | Michel Chemas | Prateek Malli
2017-05-17 | 68 | 54 | Hours Worked On the Project | 10 | 10 | 6 | 6 | 5
2017-05-18 | 65 | 48
2017-05-19 | 59 | 42
Jesaiah Prayor: Creates a simple API, Continued coding API retrieval program in order to parse required information from result string.
Deoburton Guyadin: Researched the module creation process and attempted creating sample modules, 404 Error Occurs
Elisee Augustin: Learned the SpringMVC environnment within OpenMRS.
Prateek Malli: Researched hibernate data retrieval.
Michael Chemas: Install standalone OpenMRS platform on instance of Tomcat to further understand the structure of OpenMRS, Creates Module also has a 404 Error Occur.
Sprint 4
Days | Work Left | Expected Work Left |  | Jesaiah Prayor | DeoBurton Guyadin | Elisee Augustin | Michel Chemas | Prateek Malli
2017-05-20 | 52 | 36 | Hours Worked On The Project | 17 | 17 | 17 | 17 | 17
2017-05-21 | 47 | 30
2017-05-22 | 36 | 24
Jesaiah Prayor: Continued work on API to enable search by drug name rather than id.
Deoburton Guyadin: Continued attempts to create a working module for use on OpenMRS.
Elisee Augustin: Worked on developing pages in SpringMVC for patient search.
Prateek Malli: Continued learning hibernate and SpringMVC's implemenation of hibernate.
Michael Chemas: Assisted Deoburton in understanding the workings of a module in OpenMRS.
Sprint 5
Days | Work Left | Expected Work Left |  | Jesaiah Prayor | Deoburtin Guyandi | Elisee Augustin | Michel Chemas | Prateek Malli
2017-05-23 | 29 | 18 | Hours Worked On The Project | 12 | 12 | 12 | 12 | 12
2017-05-24 | 22 | 12
2017-05-25 | 17 | 6
2017-05-26 | 9 | 0
Jesaiah Prayor: Worked on code in order to implement the National Library of Medicine API in OpenMRS module.
Deoburton Guyadin: Assisted Elisee in implementing SpringMVC code into OpenMRS module.
Elisee Augustin: Worked on bringing all segments of code together in SpringMVC for implementation in OpenMRS module.
Prateek Malli: Worked on creating code for extracting data from OpenMRS database using Hibernate.
Michael Chemas: Finalized documentation.
Complete Scrum Log
Days | Work Left (Hours) | Expected Work Left (Hours) |  | Total Hours
2017-05-11 | 85 | 90 | Jesaiah Prayor | 56
2017-05-12 | 82 | 84 | Deoburtin Guyandi | 63
2017-05-13 | 82 | 78 | Elisee Augustin | 48
2017-05-14 | 77 | 72 | Michel Chemas | 40
2017-05-15 | 75 | 66 | Prateek Malli | 34
2017-05-16 | 72 | 60
2017-05-17 | 68 | 54
2017-05-18 | 65 | 48
2017-05-19 | 59 | 42
2017-05-20 | 52 | 36
2017-05-21 | 47 | 30
2017-05-22 | 36 | 24
2017-05-23 | 29 | 18
2017-05-24 | 22 | 12
2017-05-25 | 17 | 6
2017-05-26 | 9 | 0